## Slide 1: Software Cost Estimation

## Slide 2: Software Cost Estimation
1
The Software Cost Estimation is a process of predict /estimate the approximate cost of the software project before the development starts.
Cost estimation models are some mathematical algorithms or parametric equations that are used to estimate the cost of a product or a project.
Factors considering for Project Budgeting:
      Specification & Scope
      Location
      Duration
      Project Team Efforts
      Resources

## Slide 3: Tools and techniques
1
Expert Judgment:
The experts are the people who have prior knowledge on similar kind of projects.
So they can suggest valuable insight based on their experience.
You can also take their advice on various tools and techniques that can be used to estimate similar kind of project.
Analogous Estimation:
It uses historical data from similar projects like scope, budget, duration, size, weight and complexity etc.
It measures the current project on that basis and does the estimation.
It used in the early phases of a project and is less costly, time & accurate than other methods.

## Slide 4: Tools and techniques
1
Parametric Estimation:
It analyze a past project and get the man-hours for each unit.
Then it estimate the total man-hour for the new project's activity.
It use statistical modelling technique to identify both cost and time for current project using data from past projects.
Bottom-up Estimation:
In WPS, All the project is divided into smaller work packages & cost of each work package is estimated one by one.
It estimate every single activity and rolling them up into an overall project estimate.
It is a time consuming and costly technique but it provides the most accurate estimation.

## Slide 5: Tools and techniques
1
Three-Point Estimation:
To deal with uncertainties and risk PERT (Program Evaluation and Review Technique) method is used.
Most Likely Estimate: Assuming a normal case in which everything goes as usual.
Pessimistic Estimate: Assuming everything goes wrong i.e. worst case scenario.
Optimistic Estimate: Assuming everything goes as planned i.e. best case scenario.

## Slide 6: Tools and techniques
1
Reserve Analysis:
It is important to keep the reserve budget to deal with uncertain events.
Project manager need to take approval from the sponsors for management of reserve budget.
Cost of Quality:
Includes money spent during the project to avoid failures and money spent during & after the project due to failures.
Vendor Bid Analysis:
Used to estimate what the project should cost by comparing the bids submitted by multiple vendors.

## Slide 7: COCOMO Model
1
It was developed by a scientist Barry Boehm in 1981.
The COCOMO (Constructive Cost Model) is one of the most popularly used software cost estimation models.
This model depends on the size means number of lines of code for software product development.
It estimates Effort required for project, Total project cost & Scheduled time of project.

## Slide 8: Software Project Types
1
In COCOMO, projects are categorized into three types:
1. Organic Type:
Project is small and simple (2-50 KLOC)
Few Requirements of projects.
Project team is small with prior experience.
The problem is well understood and has been solved in the past.
Examples: Simple Inventory Management Systems & Data Processing Systems.

## Slide 9: Software Project Types
1
2. Semidetached Type:
Medium size and has mixed rigid requirements. (50-300 KLOC)
Project has Complexity not too high & low.
Both experienced and inexperienced members in Project Team.
Project are few known and few unknown modules.
Examples: Database Management System, Difficult inventory management system.
3. Embedded Type:
Large project with fixed requirements of resources. (More than 300 KLOC)
Larger team size with little previous experience.
Highest level of complexity, creativity and experience requirement.
Examples: ATM, Air Traffic control, Banking software.

## Slide 10: Types of COCOMO Model
1
Basic COCOMO Model
Intermediate COCOMO Model
Complete/ Detailed COCOMO Model

## Slide 11: Basic COCOMO Model Overview
1
Key Characteristics:
It is a type of static model to estimates software development effort quickly and roughly.
It mainly deals with the number of lines of code in project.

## Slide 12: Basic COCOMO Model Overview
1
Formula:
Effort (E) : MM
Effort is measured in Man-Months (MM).
Scheduled Time (D): M
Scheduled time is measured in Months (M).
Where
E = Total effort required for the project in Man-Months (MM)
D = Total time required for project development in Months (M)
KLOC = Size of the project measured in Kilo Lines of Code
a, b, c, d = Constant parameters that depend on the type of software project

## Slide 13: Basic COCOMO Model Overview
1
Project Type | a | b | c | d
Organic | 2.4 | 1.05 | 2.5 | 0.38
Semi-detached | 3.0 | 1.12 | 2.5 | 0.35
Embedded | 3.6 | 1.20 | 2.5 | 0.32

## Slide 14: Basic COCOMO Model Overview
1
Problem Statement
Consider a software project that follows the semi-detached mode with 300 KLOC. Find the Effort estimation, Development time, and Person estimation.
Solution-
Using the constants for Semi-detached mode :
Effort (E) = = = 1784.42 PM
Development Time (D) = = = 34.35 Months (M)
Person Required (P) = = = 51.9481 Persons ≈ 52 Persons.

## Slide 15: Intermediate COCOMO Model
1
Extension of Basic COCOMO model which enhance more accuracy to cost estimation model result.
It include cost drivers (Product, Hardware, Resource & project Parameter) of project.
Formula:
Effort (E) = MM
Scheduled Time (D) = Months (M)
Where,
E = Total effort required for the project in Man-Months (MM). D = Total time required for project development in Months (M). KLOC = The size of the code for the project in Kilo lines of code. a, b, c, d = The constant parameters for the software project.

## Slide 16: Intermediate COCOMO Model
1
Effort Adjustment Factor (EAF)
EAF is calculated by multiplying the parameter values of different cost driver parameters. For ideal, the value is 1.
Product Attributes
Parameter | Very Low | Low | Nominal | High | Very High
Required Software Reliability | 0.75 | 0.88 | 1 | 1.15 | 1.40
Size of Project Database | NA | 0.94 | 1 | 1.08 | 1.16
Complexity of the Project | 0.70 | 0.85 | 1 | 1.15 | 1.30

## Slide 17: Intermediate COCOMO Model
1
Hardware Parameters
Parameter | Very Low | Low | Nominal | High | Very High
Performance Restriction | NA | NA | 1 | 1.11 | 1.30
Memory Restriction | NA | NA | 1 | 1.06 | 1.21
Virtual Machine Environment | NA | 0.87 | 1 | 1.15 | 1.30
Required Turnabout Time | NA | 0.94 | 1 | 1.07 | 1.15

## Slide 18: Intermediate COCOMO Model
1
Personnel Parameters
Parameter | Very Low | Low | Nominal | High | Very High
Analysis Capability | 1.46 | 1.19 | 1 | 0.86 | 0.71
Application Experience | 1.29 | 1.13 | 1 | 0.91 | 0.82
Software Engineer Capability | 1.42 | 1.17 | 1 | 0.86 | 0.70
Virtual Machine Experience | 1.21 | 1.10 | 1 | 0.90 | NA
Programming Experience | 1.14 | 1.07 | 1 | 0.95 | NA

## Slide 19: Intermediate COCOMO Model
1
Project Parameters
Parameter | Very Low | Low | Nominal | High | Very High
Software Engineering Methods | 1.24 | 1.10 | 1 | 0.91 | 0.82
Use of Software Tools | 1.24 | 1.10 | 1 | 0.91 | 0.83
Development Time | 1.23 | 1.08 | 1 | 1.04 | 1.10

## Slide 20: Intermediate COCOMO Model
1
Problem Statement:
For a given Semidetached project was estimated with a size of 300 KLOC. Calculate the Effort, Scheduled time for development by considering developer having high application experience and very low experience in programming.
Solution-
EAF =
Effort (E) = = = 1668.07 MM
Scheduled Time (D) = = = 33.55 Months (M).

## Slide 21: Detailed/Complete COCOMO Model
1
The model incorporates all qualities of both Basic COCOMO and Intermediate COCOMO strategies on each software engineering process.
The whole software is divided into different modules and then apply COCOMO in different modules to estimate effort and then sum the effort.
The Six phases of detailed COCOMO are:
Planning and requirements
System design
Detailed design
Module code and test
Integration and test
Cost Constructive model

## Slide 22: Example: Detailed COCOMO
1
Problem Statement: A distributed Management Information System (MIS) product for an organization having offices at several places across the country can have the following sub-components:
Database part
Graphical User Interface (GUI) part
Communication part
Solution:
The communication part can be considered as Embedded software.
The database part could be Semi-detached software.
The GUI part Organic software.
The costs for these three components can be estimated separately and summed up to give the overall cost of the system.